## Product Backlog
Product Backlog
A-maze-ing
| Hours (Individual) | Hours (By Pair)
1. Play game | 27 | 54
2. Move the ball | 23 | 46
3. Pause game | 30 | 60
4. Resume game | 20 | 40
5. Restart game | 16 | 32
6. Post time online | 17 | 34
7. Next stage | 16 | 32
Total | 149 | 298
CSc 193
Bagares, Kimberly Jay
Cadelina, Aldrin

## Sprint 1
Sprint 1: Play Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-01-12 | Downloading and installing tools and setup | 2 | 4
2015-01-13 | Distribution of hours (Schedule) | 2 | 4
2015-01-14 | Designing the UI | 1 | 2
2015-01-15 | Coding the UI | 2 | 4
2015-01-16 | Coding the UI | 2 | 4
2015-01-17 | Learning Curve | 4 | 8
2015-01-18 | Coding Functionality | 6 | 12
2015-01-19 | Unit Testing | 4 | 8
2015-01-20 | Code Debugging | 4 | 8
| Total | 27 | 54
Date | Actual | Ideal
2015-01-12 | 48 | 50
2015-01-13 | 43 | 46
2015-01-14 | 40 | 44
2015-01-15 | 36 | 40
2015-01-16 | 32 | 36
2015-01-17 | 23 | 28
2015-01-18 | 11 | 16
2015-01-19 | 3 | 8
2015-01-20 | 0 | 0

## Sprint 2
Sprint 2: Move the Ball
Date | Task | Hours (Individual) | Hours (By Pair)
2015-01-21 | Designing the UI | 1 | 2
2015-01-22 | Coding the UI | 1 | 2
2015-01-23 | Coding the UI | 1 | 2
2015-01-24 | Learning Curve | 4 | 8
2015-01-25 | Coding Functionality | 5 | 10
2015-01-26 | Coding Functionality | 5 | 10
2015-01-27 | Unit Testing | 3 | 6
2015-01-28 | Code Debugging | 3 | 6
| Total | 23 | 46
Date | Actual | Ideal
2015-01-21 | 43 | 44
2015-01-22 | 40 | 42
2015-01-23 | 37 | 40
2015-01-24 | 29 | 32
2015-01-25 | 18 | 22
2015-01-26 | 8 | 12
2015-01-27 | 4 | 6
2015-01-28 | 18 | 0
2015-01-29 | 16
2015-01-30 | 14
2015-01-31 | 12
2015-02-01 | 10
2015-02-02 | 8
2015-02-03 | 6
2015-02-04 | 4
2015-02-05 | 2
2015-02-06 | 0

## Sprint 3
Sprint 3: Pause Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-02-07 | Designing the UI | 1 | 2
2015-02-08 | Coding the UI | 2 | 4
2015-02-09 | Coding the UI | 1 | 2
2015-02-10 | Learning Curve | 4 | 8
2015-02-11 | Coding Functionality | 6 | 12
2015-02-12 | Coding Functionality | 4 | 8
2015-02-13 | Coding Functionality | 4 | 8
2015-02-14 | Unit Testing | 4 | 8
2015-02-15 | Code Debugging | 4 | 8
| Total | 30 | 60
Date | Actual | Ideal
2015-02-07 | 56 | 58
2015-02-08 | 53 | 54
2015-02-09 | 50 | 52
2015-02-10 | 43 | 44
2015-02-11 | 31 | 32
2015-02-12 | 22 | 24
2015-02-13 |  | 16
2015-02-14 |  | 8
2015-02-15 |  | 0

## Sprint 4
Sprint 4: Resume Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-02-16 | Designing the UI | 1 | 2
2015-02-17 | Coding the UI | 3 | 6
2015-02-18 | Coding Functionality | 6 | 12
2015-02-19 | Unit Testing | 4 | 8
2015-02-20 | Code Debugging | 6 | 12
| Total | 20 | 40
Date | Actual | Ideal
2015-02-16 |  | 38
2015-02-17 |  | 32
2015-02-18 |  | 20
2015-02-19 |  | 12
2015-02-20 |  | 0

## Sprint 5
Sprint 5: Restart Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-02-21 | Designing the UI | 1 | 2
2015-02-22 | Coding the UI | 2 | 4
2015-02-23 | Coding Functionality | 2 | 4
2015-02-24 | Coding Functionality | 4 | 8
2015-02-25 | Unit Testing | 4 | 8
2015-02-26 | Code Debugging | 3 | 6
| Total | 16 | 32
Date | Actual | Ideal
2015-02-21 |  | 30
2015-02-22 |  | 26
2015-02-23 |  | 22
2015-02-24 |  | 14
2015-02-25 |  | 6
2015-02-26 |  | 0

## Sprint 6
Sprint 6: Post Time Online
Date | Task | Hours (Individual) | Hours (By Pair)
2015-02-27 | Designing the UI | 1 | 2
2015-02-28 | Coding the UI | 3 | 6
2015-03-01 | Coding Functionality | 5 | 10
2015-03-02 | Unit Testing | 5 | 10
2015-03-03 | Code Debugging | 3 | 6
| Total | 17 | 34
Date | Actual | Ideal
2015-02-27 |  | 32
2015-02-28 |  | 26
2015-03-01 |  | 16
2015-03-02 |  | 6
2015-03-03 |  | 0

## Sprint 7
Sprint 7: Next Stage
Date | Task | Hours (Individual) | Hours (By Pair)
2015-03-04 | Designing the UI | 2 | 4
2015-03-05 | Coding the UI | 3 | 6
2015-03-06 | Coding Functionality | 4 | 8
2015-03-07 | Unit Testing | 4 | 8
2015-03-08 | Code Debugging | 3 | 6
| Total | 16 | 32
Date | Actual | Ideal
2015-03-04 |  | 28
2015-03-05 |  | 22
2015-03-06 |  | 14
2015-03-07 |  | 6
2015-03-08 |  | 0