## Product Backlog
Product Backlog
A-maze-ing
| Hours (Individual) | Hours (By Pair)
1. Play game | 27 | 54
2. Move the ball | 23 | 46
3. Pause game | 41 | 82
4. Resume game | 18 | 36
5. Restart game | 22 | 44
6. Next stage | 20 | 40
Total | 151 | 302
CSc 193
Bagares, Kimberly Jay
Cadelina, Aldrin

## Sprint 1
Sprint 1: Play Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-01-12 | Downloading and installing tools and setup | 2 | 4
2015-01-13 | Distribution of hours (Schedule) | 2 | 4
2015-01-14 | Designing the UI | 1 | 2
2015-01-15 | Coding the UI | 2 | 4
2015-01-16 | Coding the UI | 2 | 4
2015-01-17 | Learning Curve | 4 | 8
2015-01-18 | Coding Functionality | 6 | 12
2015-01-19 | Unit Testing | 4 | 8
2015-01-20 | Code Debugging | 4 | 8
| Total | 27 | 54
Date | Actual | Ideal
2015-01-12 | 48 | 50
2015-01-13 | 43 | 46
2015-01-14 | 40 | 44
2015-01-15 | 36 | 40
2015-01-16 | 32 | 36
2015-01-17 | 23 | 28
2015-01-18 | 11 | 16
2015-01-19 | 3 | 8
2015-01-20 | 0 | 0

## Sprint 2
Sprint 2: Move the Ball
Date | Task | Hours (Individual) | Hours (By Pair)
2015-01-21 | Designing the UI | 1 | 2
2015-01-22 | Coding the UI | 1 | 2
2015-01-23 | Coding the UI | 1 | 2
2015-01-24 | Learning Curve | 4 | 8
2015-01-25 | Coding Functionality | 5 | 10
2015-01-26 | Coding Functionality | 5 | 10
2015-01-27 | Unit Testing | 3 | 6
2015-01-28 | Code Debugging | 3 | 6
| Total | 23 | 46
Date | Actual | Ideal
2015-01-21 | 43 | 44
2015-01-22 | 40 | 42
2015-01-23 | 37 | 40
2015-01-24 | 29 | 32
2015-01-25 | 18 | 22
2015-01-26 | 8 | 12
2015-01-27 | 4 | 6
2015-01-28 | 18 | 0
2015-01-29 | 16
2015-01-30 | 14
2015-01-31 | 12
2015-02-01 | 10
2015-02-02 | 8
2015-02-03 | 6
2015-02-04 | 4
2015-02-05 | 2
2015-02-06 | 0

## Sprint 3
Sprint 3: Pause Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-02-07 | Designing the UI | 1 | 2
2015-02-08 | Designing the UI | 1 | 2
2015-02-09 | Designing the UI | 1 | 2
2015-02-10 | Coding the UI | 2 | 4
2015-02-11 | Coding the UI | 2 | 4
2015-02-12 | Coding the UI | 2 | 4
2015-02-13 | Coding the UI | 2 | 4
2015-02-14 | Learning Curve | 2 | 4
2015-02-15 | Learning Curve | 2 | 4
2015-02-16 | Learning Curve | 2 | 4
2015-02-17 | Learning Curve | 2 | 4
2015-02-18 | Coding Functionality | 3 | 6
2015-02-19 | Coding Functionality | 3 | 6
2015-02-20 | Coding Functionality | 3 | 6
2015-02-21 | Coding Functionality | 3 | 6
2015-02-22 | Unit Testing | 2 | 4
2015-02-23 | Unit Testing | 2 | 4
2015-02-24 | Code Debugging | 3 | 6
2015-02-25 | Code Debugging | 3 | 6
| Total | 41 | 82
Date | Actual | Ideal
2015-02-07 | 78 | 80
2015-02-08 | 76 | 78
2015-02-09 | 72 | 76
2015-02-10 | 68 | 72
2015-02-11 | 66 | 68
2015-02-12 | 60 | 64
2015-02-13 | 58 | 60
2015-02-14 | 53 | 56
2015-02-15 | 48 | 52
2015-02-16 | 44 | 48
2015-02-17 | 40 | 44
2015-02-18 | 30 | 38
2015-02-19 | 28 | 32
2015-02-20 | 22 | 26
2015-02-21 | 16 | 20
2015-02-22 | 14 | 16
2015-02-23 | 8 | 12
2015-02-24 | 4 | 6
2015-02-25 | 0 | 0

## Sprint 4
Sprint 4: Resume Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-02-26 | Designing and coding the UI | 3 | 6
2015-02-27 | Coding Functionality | 6 | 12
2015-02-28 | Unit Testing | 4 | 8
2015-03-01 | Code Debugging | 2 | 4
2015-03-02 | Code Debugging | 3 | 6
| Total | 18 | 36
Date | Actual | Ideal
2015-02-26 | 27 | 30
2015-02-27 | 17 | 18
2015-02-28 | 8 | 10
2015-03-01 | 5 | 6
2015-03-02 |  | 0

## Sprint 5
Sprint 5: Restart Game
Date | Task | Hours (Individual) | Hours (By Pair)
2015-03-03 | Designing and coding the UI | 4 | 8
2015-03-04 | Coding Functionality | 6 | 12
2015-03-05 | Unit Testing | 6 | 12
2015-03-06 | Code Debugging | 6 | 12
| Total | 22 | 44
Date | Actual | Ideal
2015-03-03 |  | 36
2015-03-04 |  | 24
2015-03-05 |  | 12
2015-03-06 |  | 0

## Sprint 6
Sprint 6: Next Stage
Date | Task | Hours (Individual) | Hours (By Pair)
2015-03-07 | Designing and coding the UI | 4 | 8
2015-03-08 | Coding Functionality | 6 | 12
2015-03-09 | Code Debugging | 10 | 20
| Total | 20 | 40
Date | Actual | Ideal
2015-03-07 |  | 32
2015-03-08 |  | 20
2015-03-09 |  | 0